## Test Plan
Timelines | Month : 1 |  |  |  |  | Month: 2
| Week 1 11th Dec-15th Dec | Week 2 18th Dec-22nd Dec | Week 3 25th Dec- 29th Dec | Week 4 1st Jan-5th Jan | Week 5 8th Jan -12th Jan | Week 6 15th Jan-19th Jan | Week 7 22th Jan-26th Jan | Week 8 29th Jan-2nd Feb | Week 9 5th Feb -9th Feb
Activities
Requirements Gathering
Acquire KT/Understand Requirements
Test planning
Test planning & Prioritization
GATE: Review Deliver Test plan and get the approval
Manual : Test Case Designing
Amigo app and Ebike Test Case Creation
Deliver Test Case and get the approval after review
Test case Execution Amigo App Android & iOS , Ebike
Bug reporting [Exploratory and Failed Test Cases]
Defect Fix validation / Sign Off
Reports
-Daily Status Report ## -Weekly Connect ## -Monthly Test Reports ## - Final Test Summary Report ##

## Day Wise Plan-Resource Loading
Resource Loading |  | Duration |  |  | Resource
|  | Month | Week | Day | Planned Work
Total Resource : 1 |  | 1 | 1 | 2023-12-11
Manual QA : 1 |  |  |  | 2023-12-12
Activities | Color Legends |  |  | 2023-12-13
Requirements Gathering |  |  |  | 2023-12-14
Acquire KT/Understand Requirements |  |  |  | 2023-12-15
Test planning |  |  | 2 | 2023-12-18
Test planning & Prioritization |  |  |  | 2023-12-19
GATE: Review Deliver Test plan and get the approval |  |  |  | 2023-12-20
Manual : Test Case Designing ,Review & Execution |  |  |  | 2023-12-21
Amigo app and Ebike Test Case Creation |  |  |  | 2023-12-22
Deliver Test Case and get the approval after review |  |  | 3 | Holiday
Test case Execution |  |  |  | 2023-12-26
Bug reporting [Exploratory and Failed Test Cases] |  |  |  | 2023-12-27
Defect Fix validation / Sign Off |  |  |  | 2023-12-28
Reports |  |  |  | 2023-12-29
-Daily Status Report ## -Weekly Connect ## -Monthly Test Reports ## - Final Test Summary Report ## |  |  | 4 | 2024-01-02
2024-01-03
2024-01-04
2024-01-05
|  |  | 5 | 2024-01-08
2024-01-09
2024-01-10
2024-01-11
|  | 2 |  | 2024-01-12
|  |  | 6 | 2024-01-15
2024-01-16
2024-01-17
2024-01-18
2024-01-19
|  |  | 7 | 2024-01-22
2024-01-23
2024-01-24
2024-01-25
|  |  | 8 | 2024-01-29
2024-01-30
2024-01-31
2024-02-01
2024-02-02
|  |  | 9 | 2024-02-05
2024-02-06
2024-02-07
2024-02-08
2024-02-09