## Sheet1
PRD | Test cases count | Priority 1 | Priority 2 | Priority 3 | Status | Rough data data for Test case design | Requirements
Onboarding & profile creation | 116 |  |  |  | Need to review the test cases
Home page | 50+ |  |  |  | On -progess | Need to design more than 100+TC | Goals , social feeds,Activities , your ride details ,challenge with the friends ,compass ,contextual home cards ,Bike state,connectivity ,garge screen ,App push notification
Connectivity |  |  |  |  | Yet to start | Need to design more than 60+ Tc | Instruction page connectivity ,Existing user connectivity ,error conditions ,Capp Vs connetivity
Maps |  |  |  |  | Yet to start | Need to design more than 80+ Tc | New user experience ,Main maps screen, Search bar screen ,Quick Access Screen display, Saved routes Screen,Navigation Screen in Fast mode,Notification related to Maps, Plan your ride screen
Engineering modes |  |  |  |  | Yet to start | Need to design more than 30+Tc | 4 modes , Engineering mode data's are merged in garge screen on the home page .
Ride details, stats & history |  |  |  |  | Yet to start | Need to design more than 100+TC | New User experience, Existing User Experience , Ride History, Ride Details, Overall Ride Stats
Rough data - 370 + Test cases need to written
10 days / if 40 test cases written