## EV
Sl.No | Project Name | TL/Manager | Team Size | Testing scope/Application Details | Client POC | Delivery details from Jan - March | Project challenges | Future roadmap | Delivery Partner | Testing Best practices implemented
1 | Tag- Mango | Jyesh | 1. Mahesh(M) 2. Rehmat(A) 3. Sunil(A) 4. Imran(M) | Testing Scope: 1. End To End Testing for Base and WL Product 2. Platform Coverage - Web , Mobile App and PWA. 3. Automation 4. Product Documentation Application Details: TagMango is the easiest and the most cost-effective platform for creators to host live workshops, pre-recorded courses, and build memberships | Hassan | 1. We embraced the "Think Automation First" concept, aiming to minimize manual tasks and maximize automation. 2. Utilizing the test case studio tool, we were able to create over 800 test cases within a 20-day timeframe, significantly reducing manual effort. 3. The artifacts generated by the test case studio tool expedited test documentation processes. 4. We revamped the test case dashboards and bug dashboards for enhanced visibility to our client stakeholders. 5. Introducing "QAautomater," scriptless automation tool, allowed our manual engineers to automate scripts across multiple platforms(Mobile, web and API) effortlessly. Integration with Browserstack provided comprehensive multi-device coverage. 6. Various test processes were implemented, including knowledge transfer (KT) and reverse KT processes, test planning, weekly client demonstrations, regular sharing of Weekly Status Reports (WSRs), publication and demonstration of automation reports, and defect tracking for priority resolution. |  |  |  | 1. Automation First Approach 2. Used Testcase Studio for designing test case 3. Used QA Automater scriptless automation to automate cases 4. Mind Map Approach for testing
2 | Auto-Pe | Jyesh | 1. Rajeshwari(M) 2. Rupesh(A) | Testing Scope : 1.Backend API testing 2.Maintaining Test case repository on Mpay 3.Platform coverage : Backent API testing and UI testing 4.Designing test cases on APIs 5.Regression testing on UI (Coin service) 6. End to End automation for all user journey Application Details: Mpay is a redirecting customers to MPay from various platforms and implementing rule-based algorithms for managing charges, discounts, and deductions. MPay is a Payment Gateway focusing on core domain features with differentiated rules and algorithms, ensuring seamless transactions With a robust Rule Engine and comprehensive API integrations, MPay facilitates various payment options, promotions, and notifications, while efficiently managing transaction. | Pooja | Worked on rule engine APIs and Merchant APIs 1. Total Test Cases Designed: 136 2. Total Defects Logged: 15 3. Platforms Covered: AutoPe API and Coin UI 4. Framework Creation for handling UI and API cases Closed 1 Open position - After providing API training to rupesh Test Plan is in progress will be closed this week | Frequently changing APIs request parameters UI functionality is changing frequently. | Work on Rule Merchant APIs of end-to-end flow testing Manual and Automation |  | Going the PRD and Understand the requirement well, as per the requirements designing test cases . If any changes has done in PRD As per the latest update , maintaining documentation and designing the test cases and excute the test cases as per requirements.
3 | E-Motorad | Jyesh | 1. Karthikeyan Kumaran(M) | Testing Scope: 1. Designing Test cases for Frontend, Backend (API &database), and hardware Testing. 2. Sanity Testing for New builds 3. Regression Testing For Frontend and Backend 4. Performing API load Testing using JMeter Application details: Designing separate applications for E-bikes, which include the features of Bluetooth pairing, Navigation, and ride dashboard screens. Able to create goals and track the ride history and ride stats of the user and Separate settings for the child mode option. | Jagrit,Gaurav Gupta | -Reviewing All the features of PRD [Product requirement document] and start designing test cases for all the Features. -Designed test cases for Frontend, Backend(Postman &Database) &Hardware (E-bike). -Performing sanity testing for New builds [Weekly two to Three builds] -Done Regression testing for Alpha Release executing 600+ Test cases -Total designing test cases for Regression for Alpha Release -Frontend – 699 -Backend – 237 -Hardware – 41 -For Beta release executing 450+ test cases. -Executing test cases for Alpha and beta internal releases. -Performing API load tests using JMeter. -Raising issues and resolving issues as per the resolutions provided by the developers Issue count : -Alpha Release Bug count - 63 -Beta Release Bug count -202 (20-03-2024) -Total count -265. Once Existing bugs got fixed and bug verification was done for more than 180+ bugs. | Updating the feature list frequently Adding and Removing the features without much updates. Testing device availability | For Alpha and Beta Releases covering up to R2 features alone, As per the EMotorad feature list plan it will be up to R7 Release and adding up the new features into the list. |  | After Reviewing the PRDs and setting the Test estimation plan for the Alpha Release Due to time constraints parallelly designing and executing test cases for Alpha Release Due to new features implementation designing and executing test cases parallel Reporting Bugs on frontend, backend and hardware The client was requested to do load testing for Beta Release, scale up the skills, and done API Load test using JMeter
4 | Ola | Vijay | 1. Ashwin(M) 2. Yashwant(M) 3. Darshan Mesta(M) | Testing Scope: E2E OMS(Order management System, EV Purchase FE+ BE Application Details: Ola is a well-known ride-hailing company operating in India. It provides convenient transportation services through its app, connecting passengers with drivers. | Vivek AR | 1. Multiple Patch Release with enhancements and hot fixes [EDD(Estimate Date of Delivery), Brand Champion Flow, HCFC - Hypercharger Fast Charger] 2. B2B End to End testing and Enhancements testing | 1. Less time given for QA activities 2. Last minute Changes 3. Lack of PRDs and Figma Updation , for some feature these documents are not at all there 4. No walkthrough given to QA before deployment features 5. Communication GAP between DEV , Product and QA (Product directly give suggestion to DEV) 6. Poor Bug Fix most of the time one bug fix led to multiple re-open of issues | 1. Auto and Bike Launch 2. B2b multiple Varient Choice |  | 1. Uniform test case template across the PODs 2. Bug Traige on Daily basis 3. Mandatory Sign Off Process
5 | Ola EV | Vijay | 1. Prashant B(M) 2. Darshan(M) 3. Sanjay (M) 4. Srinidhi(M) 5. Sujith(M) | Testing Scope: E2E CAPP + EV + Backend Testing [Manual + Automation] Application Details: Ola Electric is a subsidiary of Ola, focusing on electric mobility solutions. Ola Electric produces electric scooters | Prabhanjan | 1. S1 X Plus Scooter variant Testing - Through testing of CApp, Scooter and Backend 2. Dux Feature Tesitng - FE and BE 3. Multiple Patch Release with enhancements and hot fixes 4. 4.0.0 release to customers on basis of whitelisting 5. App changes having the feature of BE control on every feature through flags 6. Improvemet on Maps SDK 7. Moved the PWA screen features to native app 8. Compatability testing 9. Integrated and restructed the application which will work for all the variants of OLA scooter(5variants) | 1. Vehicle Availablity : 2. Less time given for QA activities 3. Scooter Build given to CApp team without integration testing (Capp+Scooter) 4. No STLC - Everything task comes on adhoc basis | 1. Move OS 5.0 for Scooter 2. Three Wheeler Vehicle Launch 3. OLA Bikes 4. Exploring Purchase Flow in CApp |  | 1. Encorporated Mobile App performance using Android Studion- Profilers[Memory and CPU Utilization] 2. Helping Team in Designing Product based logical test scenarios 3. Took a leadership of the platform(Android) and prepatred the test plan for every release and reduced the effort and increased the productivity 4. Initiated performing monkey testing to find the undiscovered crashes before every release 5. For the accuracy in testing invetsed effort and collected the readings for the MAP feature on riding the scooter

## Digital, CMI
Sl.No | Project Name | TL/Manager | Team Size | Testing scope/Application Details | Client POC | Delivery details from Jan - March | Project challenges & Mitigations | Future roadmap | Delivery Partner | Testing Best practices implemented
1 | Lyca Digital | Deepak | Team of 7 - Chandrashekar Reddy ( M) - Santhosh Kumar S ( M) - Santhosh M( A) - Sridhar ( A) - Krushna chandra jena( A) - Rajeswaran(A) - Deepak P( M) | Test scope : Manual and automation testing Platform : App, Website , Msite Application details: Lyca digital is a prominent Europe based telecom company providing mobile services to millions of customers across Europe, US, Australia, Asia. The company embarked on a comprehensive digital transformation initiative to modernize its operations and enhance customer experiences, it has recently revamped its mobile app and website to enhance the user experience and introduce new features for more than 16 countries. | Anurag, Abhishek , Nagaraj | Manual 1.Performed feature testing on Android and iOS for below stories along with regression testing for 16 countries -Revert the Happy holidays Splash screen -Switch Account -Improved UI journeys / Simplified -Scan Lyca Voucher with QR Code - Top-up Option -Transfer Auto renewal from one card to Another -PayPal Integration (Direct) -Maintains screen on mobile apps -Update card from My Account -Lia Chat BoT 2. Created test cases for new feature releases 3. Performed E2E testing for new country Ukraine prepaid on Android and iOS 4. Performed E2E testing on Postpaid UK & NL. Automation 1.IOS Framework implementation with required driver initialization , server initialization & Data parameterization etc. 2.Lambda integration for iOS. 3.Implemented functionalities like screenshots and generic exceptions and execution logs for iOS & Android. 4.IOS regression completed for 5 countries. 5. IOS Smoke and sanity completed for 16 countries. 6. Monitoring suite for all 16 countries in both App, Website and M-site | Challenges 1) No proper QA process set up and implementation 2) Timelines for testing are decided on ad hoc basis and proper release process is not maintained. 3) Mis-communication between internal client, Dev team and QA 4) Build details are not shared in advance and team won't be aware of changes until last minute Mitigation plan 1) We have discussed the above issues with clients and made them understand the importance of the challlenges faced. | Overall 1. Belgium postpaid mobile app release planned for this month 2. Features implemtation ( reedem vocher scanner and payment auto renewel transfer, Paypal integration) for all 16 countries 3. Postpaid app releases for other countries Automation 1) My account - phase 3 automation for web and msite 2) Postpaid app automation for andriod and ios for all released countries 3) API automation 4) Pospaid web automation for all release countries | Lavanya | 1. Defect traige meetings on a daily basis 2. Test cases creation , review and feedback 3. Weekly and daily status reports 4. QA sign off reports Automation 1) Prepared automation plan in detail with ETA and shared it with clients 2)Regular code review with internal members and clients 3) lamdba integration for parallel execution for 16 countries for web, mobile, msite 4) Jenkins integration with email notififcation on a daily basis 5) Sanity execution on live build everyday and reports stored on cloud 6) Regular maintaintance of our code for stablility 7) Framework documentation and demo shared to internal team and provided KT.
2 | VIL | Squad leads and prem | Team of 12 Web Squad: [Team size 3] Mailarappa Bani ,Rashmi Rajput and Gajanan Patle Neo: [Team size 3] Deepak Jadhav, Divya K, and Lavanya K. App Squad: [Team size 2] Atul Kale and Shrredhar Sb Payments Squad: [Team size 2] Prem J and Shahsnak Digital Store - Market Place: [Team size 2] Sunil Barigala & Shital Mache | Test scope Web Squad: Manual Testing Neo Team: Manual [UAT] / Automation [Frontend] App Squad: Manual,API,Mobile testing Payments Squad: Manual [UAT] Digital Store - Market Place: Manual, Web, API, Mobile testing Application Details Web Squad: Vi brings you the best mobile rechargeoffers with unlimited calling and daily data for seamless connectivity. Avail exclusive online recharge offers via the Vi App or website and enjoy a world full of benefits such as Short/Long-Term Validity, Unlimited Night Data, Data Rollover, Data Delight, access to multiple OTTs, and much more with Vi online recharge offers. Pay bills online and avail postpaid bill payment offers with Cred Pay, Amazon Pay, Paytm, MobiKwik, LazyPay, etc. Vi postpaid bill offers include assured cashbacks and other discounts on eligible transactions. Cashback would be credited to respective UPI wallets or via scratch cards. Enrol for autopay to automatically pay postpaid bills online. Neo Gold Squad: NeoGold is part of the VIL Website and If any customers want to take a new connection from VIL then this module helps customers/users to get any kind of new product available on the VIL site. They can buy new prepaid or postpaid connections etc by creating orders on site. And we have a call center dashboard that helps agents to connect with new users. Neo Lite Squad: The NeoLite app is a one-stop destination for VI digital Sales Partners for digital KYC at the customer's doorstep. Neo Lite enables our partners to activate Prepaid and Postpaid customers without any paper using Digital KYC / Electronic KYC. Zero documentation hassle, Almost Instant customer activation, and Safe and secure Authentication. SKYC Squad: SKYC - End-to-end development for the KYC opting for the Prepaid and Postpaid Sim. From Ordering the SIM until the SIM is delivered. App Squad: Vi App lets you conveniently get online mobile recharge, pay postpaid bills, order a new SIM, enjoy music, games,live TV, set callertunes Payments Squad: App payments combines the convenience of Autopay for recharges, a personalised Own payment page(OPP), and a versatile utilities feature. User can seamlessly manage in and out payments, benifiting from time-efficient transactions, centralized transaction management,and a user friendly interface, positioning the VIL app as a comprehensive solution for a spectrum of financial needs. Digital Store - Market Place: Vi Shop is module integrated in Vi App with access to users for wide range of giftcards and can do bill payments across which is being called internally as Digital Store and being maintained using a CMS tool called Market Place backing by Headless API provided by LifeRay | Vodafone Idea Limited (Anupama) | Payment - Web payments - Utilities ( electricity , Loan repayment , water, Landline, broadband - Major release testing in completed App payments - Postpaid auto pay, other adhoc changes , Release testing is completed App - Successfully done with Release 43, which is on February 15th, and there are a total of 70 US items in scope. Successfully delivered with Release 44,which is on march 7th and 49 US items are in scope. Neolite: 1. Completed Postpaid POS onboarding demand UAT before the deadline given by the Business team and defect count is also more as compared to SIT team. 2. Successfully deployed Postpaid POS onboarding demand on production with no major issues. NeoGold: 1. Reported payment related issues of SKYC on production and it is resolved by 24hrs time. 2. We have given automation test cases to SIT team and it was updated successfully and reflecting on production. Web In last sprint 14[Ended on 27th Feb] tested almost 21 user stories - One production issue was reported with priority p3 Related to Web sprint 14 we have reported 12 issues from UAT in staging environment | Challenges Challenges and solutioning presentation is given to Ashish, Nik and Anupama | Roadmap from delivery 1) Streamlining process across each PODs 2. Defect Leakage reports, Squad Dashboards are ready, meeting with anupama on 21st to showcase and discuss 3. Implementing the reports across squads 4. Scriptless automation demo to be planned with Ashish and other stakeholders 5. User testing solution- Oprimes demo to be planned. 6. Monthly governance call with business stakeholders to be setup. |  | 1. Bug traiage call with respective Product owners and Anupama 2. Involved in all requirement call to understand the US and clarification of doubts 3. Sharing the regular update to clients via WSR and KPI calls
3 | D-Mart | Gayathri Priyadharshini | Team of 4 Gayathri Priyadharshini,( M) Richa Agarwal (M) Hari krishna ,( A) Yash Mulukar ( A) | Test scope : Manual, API . Automation : Api, Front end , Mobile Appium" Application details : Dmart - PWP Application , Quick Fill , Store Receiver, Vendor Report, Purchase order. Sortation - In Progress, Sorter - This application will use on warehouse to implement the bulk picking of the product and put it in conveyor belt(e.x Airport) , those picked item , will go into different store (350+) . We are integrating this application to third part vendor Bastian solutions . | Hari Krishna, Ashish Dadhwal | Manual Team is started working on sortation module testing and tested around 20 userstories , 25 Userstory testing is in progress Testcases creation is in progress for sortation module Quickfill application released to UAT - mobile app Tested 4 new stories and 4 enhancement for PWP with box application Automation Team Started to work on the Quick Fill Application for new changes QF Application - Created scripts on offline mode Modifing the script and verifying on HHT Device Sortation - Create Delivery part , started to Automate the test case Automation progress Quick fill - completed, sortation - Inprogress | 1) Resource crunch | Delivery roadmap 1) Gayatri to be moved as Sr.Lead role. 2) 2 new resource requirement needs to be fulfilled. Project roadmap 1. QA team resource can be increased as they are expanding the team. 2. Planning for multiple project execution - Purchase order, POS application ( billing) |  | 1. Maintaining Test scenario document and deriving the testcases 2. Test Scenario review and feedback from clients 3. Bug tracking and triage through Jira 4. QA sign off reports after every release
4 | Lokal | Pinki | Team of 5, Pinki Kumari, Pawan Dhakar, Ravuri Sri ranga Chandana, Nandhini Vulli, Likhith.V | Test scope : Manual (FE/BE)/API/Charles/Flipper Application details : Media/ Jobs/ Realestate/Ads Lokal is a content, classifieds & community app that helps you find the latest local content updates, and search for jobs in your area for absolutely free now! Available in your language, you don't have to hunt anywhere else. Indeed, it is the perfect place for anything local! More than 2 crore Indians trust Lokal App 🇮🇳 Made in India app rated for top Telugu, Tamil, Kannada, Marathi, Malayalam, Gujarati, Punjabi, & Bengali updates. Hindustan’s national stories come to your fingertips. | Vipul Choudhery(CTO) and Jani Pasha (CEO) | 1. Major releases tested for Jobs and navigation pod 2. Gyani app testing is started | 1) Resource crunch and limited time for testing 2) Limited device for testing due to this not able to find device specific issues. Mitigation 1) Requested client for increase the team size for better quality 2) Proposed automation tool, currently doing feasibility study | Delivery roadmap : 1) 1 New requirement for production support testing needs to be fulfilled 2) Need to implement automation via tool / scripless solution. Project roadmap 1) They are planning for many apps launch in upcoming months , Hence we can expect the new req from client |  | 1. Bug tracking and triage through Jira 2. QA sign off reports after every release 1
5 | Aveva | Brajesh | Team of 4, Brajesh Thakur - Lead Bushra Khalid - Senior Test Engineer Prakash Hiregoudra - Senior Test Engineer Sushma - Buffer | Test Scope 1. Manual test 2. API 3. SalesForce - ServiceCloud Platform : 1.Web 2. Android, 3. iOS. Application details 1 - (GCSWeb)- Web Application where its currently migrating to the Expirence Cloud, rapid changes as per new buisnes requirements Saleforce ServiceCloud Test from the Backend 2 - (Flex) - Subscription based Web Application which is growing rapidly, Continuous Development- Testing,New changes as per Buisness Requirement, Functional Test. | Navnit, Syam | 1. Experience cloud testing is started and tested more than 20 requirements, team is collobarating with accenture team. 2. 3 maintainance release happened for GCSWeb without any major prod issues 3. Upon kris request, Did a small POC on playwright tool for flex and presented to Kris and team. | No major challenges as of now Previous challenges related to WFO and team communication has been resolved. | Overall 1) To complete experience cloud project by June in colobaration with accenture 2) Major changes in GCSWeb ( design and architecture change) in next months Delivery roadmap 3) Initiate all QA process once the experience cloud implementaion project is completed from accenture team. |  | 1) Requirement mapping with testcases, Bugs in Azure devops 2) Test cases restructuring is been initiated 3) Regular QA bi weekly and monthly meeting for continous feedback and improvement 4) Bi weekly reports and presentation to clients on progress update 5) QA sign off for every releases 6) Prepared requirement gaps report for experience cloud which will be discussed with business stakeholders
6 | Eshipper | Sandeep | Team of 2 Sandeep namitha | Test scope Manual testing Platform : Web application and testing on Mobile web(Android,iOS) Application details : An Intuitive Platform, Built to Streamline Your Orders The faster, simpler way to integrate, manage and ship all the eCommerce orders | Nishant Varshney(Founder and Technology Head) Sarthak Pandiay(Project Manager) | Testing done for major deployment -Sanity, smoke on test environments and PROD after each deployments(every week minimum 2-3 deployments) -Issues Retesting -Modules testing after each enhancements are implemented -Issues logging after finding a bug and informing in the internal group there itself instead of waiting till EOD | Project challenges: -Sanity, smoke on test environment and PROD after each deployments in short notice and completion in short time. -Before completion of sanity on testing environment there will be a deployment on prod -Sometimes doing sanity on test envs and prod on same day | Project roadmap: -Enhancements implementation -Testing enhancements Delivery Roadmap -API testing -Chances of automation
7 | Wizikey | Pinki | Alfan | Test Scope Manual testing Platform : Web application and testing on Mobile web(Android,iOS) Application details Wizikey saves time by bringing relevant brand mentions from news, blogs, podcasts and other mediums in one place. It provides insights to build better awareness. It is built by communications' professionals who struggled with excel sheets, clunky software and decided to solve it themselves. | Anshul | Hotfix,New Category in Story Type called Authored Articles and CSM Data on Admin Side on Workspaces & Campaigns Table testing is in progress Sprint 20 release testing in progress | Alfan has resigned and the client is yet to extend the SOW
8 | Peoplebox | NA | Sidiqua | Test Scope Manual testing Application details : PeopleBox integrates with all work tools(SQL,JIRA,Hubspot<Asana,Slack etc) to make real-time goal tracking and business review magically easy. | Alagu | 1. Enable review screen sidebar for Custom Reviewer Total bugs raised: 05 2. Custom Text Column in Calibration Total bugs raised: 33 3. Enable goals in custom review types. Total bugs raised: 03 4. Custom Text Column in Calibration Total bugs raised: 28 5. Add UI support for adding custom reviewers from reviewee management Total bugs raised: 07 6. Peer Restriction checkbox input in UI Total bugs raised: 08 7. Customer issue: Add score visblity to Goals Total bugs raised: 01 8. Custom Attributes - Unique question_ids Total bugs raised: 06 9. Competency Themes in Web Total bugs raised: 11 10. 360 degree review Total bugs raised: 06 11. Some Frontend legacy issues: 13 | Project challenges 1. QA weren't involved during feature walk through, After dev code completion QA get to know what's the requirement 2. No time to write/prepare testcase as QA where targeted to start with testing and to release in short time 3. Impacted areas not mentioned before start of testing
9 | Red-Bus | NA | Team of 2 - Rashmi Nayak Sowmya Gosi | Test scope Manual Testing (Frontend Testing) | Chandrashekhar Patil | 1. Went live for International geos(Peru, Columbia, Indonesia, Singapore, Malaysia) rubicon home screen for android and iOS channels 2. Designed test cases for SRP International geos. 3. Designed test cases for Accounts India. 4. Went live for Streaks India in android, iOS, Web, MWeb channels. 5. Helped in track stories such as Gender validation on Mweb, test case execution on RTC auto expand web. 6. Started testing for SRP international geos. | Delivery challenges 1. Soumya is going on marriage leave for 1 month, We need to find her back up - Mitigation ( can be placed someone from bench) 2. Single person testing both andriod and Ios Project challenges 1. Design gets updated and we will not be informed at times. 2. While testing rubicon screens need to check existing production as well as design and if there is any discrepancy need to get confirmation from product/ design which will take time. | Project roadmap 1. Releasing SRP for all geos. 2. Accounts testing for India. 3. Payments, Seat Layout, Cust Info and Bus Buddy test case design and testing for all geos. |  | 1. Bug tracking and triage through Jira 2. QA sign off reports after every release
10 | QuickPlay | NA | Bhanu Chaitanya abbaraju | Test scope Manual and Automation. OTT doman testing, Video testing, API manual and automation Google Big query . Basic knowedge on automation for mobile and web | Prasad Kolisetty - CEO/Srikanth Rao - Head of Media Strategic Industry Sales | 1. Deliverying bug free prodcut for 16 platforms across 7 customers with provided time and tight deadlines 2.API automation intial phase is done one customer 3.Evaluation of client suggested tool TestIM and started using it across multiple projects and builds 4.Working on next generation client product validation with all cloud technologies like Google Big query ,GraphQL 5.Performance testing is done with locust tool using python | No major challenges as of now